## Sheet1
Vit Prechtl (C00298335) - Procedural Building Generator |  | SEP | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR
PHASE | DETAILS | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25
Project Initiation | - Initiation -Project Proposal | SEP WEEK 1: Project Proposal
| - Initiation - Proof of Concept | OCT WEEK 2: Proof of Concept
| - Initiation - Technical Proof of Concept | OCT WEEK 3: Technical PoC
| - Initiation - Storyline | OCT WEEK 4: Storyline
| - Initiation Gantt Chart | OCT WEEK 4: Gantt Chart
Geometry Nodes Main Framework | - Geo nodes - Develop building generator based on modeled walls | OCT WEEK 5: Modeled Walls
| - Geo nodes - Implement the building generator to work on modular walls | NOV WEEK 6: Modular Walls
Assets | - Assets - Create concept for 3 base asset packs | NOV WEEK 7: Concept 3 asset packs
| - Assets - Model the 3 base asset packs | NOV WEEK 8: Model 3 asset packs
| - Assets - Unwrap and texture the 3 base asset packs | DEC WEEK 10: Texture & Unwrap 3 asset packs
Geometry Nodes Optimisation and Fixes | - Geo Nodes - Implement seed-based randomisation | DEC WEEK 12: Seed random
| - Geo Nodes - Integrate, optimise the tool, fixing issues | DEC WEEK 13: Integration + Fixes
Python User Interface | - Python - Develop Python interface and Blender sidebar addon | JAN WEEK 14: Python User Interface + Sidebar
| - Python - Addon, Finetunning, debugging | JAN WEEK 17: Addon Finetuning + Debugging
Presentation | - Presentation - Generate example buildings, assemble environments | FEB WEEK 20: Generate examples
| - Presentation - Lighting, rendering and presentation visuals | FEB WEEK 20: Presentation visuals
| - Presentation - Documentation, evaluation and final submission | SEP WEEK 1: Documentation + Evaluation + final submission (Documentation weekly)